## RT Main Menu
Risk Treatment Tracking
Developed by: Georgi Popov, Ph.D., QEP, SMS, ARM; and Bruce Lyon, CSP, PE, ARM, CHMM
University of Central Missouri and Hays Companies of Kansas City
v. 1.0 / 1/1/18 ® 2018
Gantt Chart
Milestone Chart
Thermometer Chart
Main Menu
Risk Tracking Template

## Risk Tracking
Risk Treatment Tracking Template
| Risk # | Risk Description | Priority (High, Medium, Low) | Start date | Activities | Timeframe | Cost to prevent or mitigate risks | End Date
1
2
3
4
5
Developed by: Georgi Popov, Ph.D., QEP, SMS, ARM; and Bruce Lyon, CSP, PE, ARM, CHMM
University of Central Missouri and Hays Companies of Kansas City
v. 1.0 / 1/1/18 ® 2018
Main Menu

## Gantt Chart PtD Project
PtD Project Timeline
| Activity | Days Since Start | Days Left for Completion
| Start Date 3/27/2017 - Form Team |  | 1
| Literature Review - Planning | 1 | 7
| Identify/develop Mapping/Flow Diagrams | 8 | 97
| PHA | 105 | 70
| Risk Assessment | 175 | 15
| PtD Control Measures or Risk Treatment | 190 | 14
| Implementation | 204 | 7
Developed by: Georgi Popov, Ph.D., QEP, SMS, ARM; and Bruce Lyon, CSP, PE, ARM, CHMM
University of Central Missouri and Hays Companies of Kansas City
v. 1.0 / 1/1/18 ® 2018
Main Menu

## Milestone Chart
Date | Activity | Date | Activity | Text Placement
2017-01-01 | Planning | 2017-01-01 | Planning | 10
2017-02-01 | PHA | 2017-02-01 | PHA | -10
2017-03-01 | Risk Assessment | 2017-03-01 | Risk Assessment | 10
2017-04-01 | PtD Control Measures | 2017-04-01 | PtD Control Measures | -10
2017-05-01 | Implementation | 2017-05-01 | Implementation | 10
2017-06-01 | Testing | 2017-06-01 | Testing | -10
2017-07-01 | Re-assessment | 2017-07-01 | Re-assessment | 10
2017-08-01 | Project Approval | 2017-08-01 | Project Approval | -10
2017-09-01 | Project Completed | 2017-09-01 | Project Completed | 10
Formulas:
Date = IF([Date]<>"",[Date],"")
PtD Project Milestone Chart
Project Completed
Main Menu

## Thermometer Chart
Actual % Risk Treatement Project Completion | Target % Completion
70 | 100
Main Menu

## Bal SC
Metrics Balanced Scorecard
Results
| Objective | Metric | Target | Weighting | Q1 | Q2 | Q3 | Q4
1 | Reduce TIR 70% | OSHA TIR | < 1.0 | < 1.0 = 5 pts | 3
< 1.2 = 4 pts
< 1.4 = 3 pts
2 | Reduce Ergo Illness to zero | # non-recordable ergo cases | Q1<5 Q2<4, Q3<3, Q4<2 | On-plan = 5 pts | 5
3 |  | # recordable ergo cases | Q1<2, Q2<2, Q3=0, Q4=0 | On-plan = 5 pts | 5
4 | BOS trng | % completion | 100% by end Q1 | On-plan = 3 pts | 3
| BOS Implementation | % completion | 100% by end Q2 | On-plan = 3 pts
5 | Ergo aid Trng | % completion | 100% by end Q1 | On-plan = 3 pts | 3
| Use of ergo aids | % of Observations | 80% by end Q3, 100% by end Q4 | On-plan = 3 pts
6 | Engineer trng | % completion | by end of Q1 | On-plan = 2 pts | 2
| Automation Installation | % of tool complete | 50% by end Q2, 100% end Q4 | On-plan = 5 pts
7 | Annual LOTO Inspections | % completion | 25% per quarter | On-plan = 4 pts | 4
|  |  |  | Points possible= | 27
|  |  |  | Total Score | 25
|  |  | Target 90% | % Score | 92.59%
0.92593
Business Operations Strategy (BOS)